# CONCEPT NOTE: Africa’s AMR Decade Review: A 145-Day Stocktake to Inform Evidence-Driven Commitments for the Global AMR Agenda

### Nigeria + Six African Countries | 2024–2025 AMR Conference Cycle

## 1. Background and Rationale

Nearly a decade after the adoption of the Global Action Plan on Antimicrobial Resistance (AMR), African countries have made substantial—but uneven—progress in building surveillance systems, strengthening laboratory capacity, improving stewardship, and advancing One Health governance. Despite these gains, AMR continues to threaten health security, food systems, environmental integrity, and economic stability across the continent.

Nigeria, as one of Africa’s largest health systems and a regional leader in AMR governance, is uniquely positioned to drive a continental stocktake that assesses:

- How investments since the Global Action Plan have translated into operational capacity

- The extent to which AMR data is being used for policy and regulatory decision-making

- The degree of One Health integration across human, animal, and environmental sectors

- What implementation-sensitive course-corrections are needed to accelerate progress

- How African countries can align with the Troika process and global AMR priorities

This 145-day initiative will culminate in a high-level presentation at the AMR Conference, supported by a structured 10-day publication cycle to maintain visibility, transparency, and political momentum.

## 2. Goal of the Initiative

To conduct a comprehensive, evidence-driven AMR stocktake across Nigeria and six additional African countries, generating actionable insights and political commitments that strengthen Africa’s positioning within the global AMR agenda.

## 3. Objectives

### i. Evidence Review

Assess how a decade of AMR investments across human, animal, and environmental sectors has translated into:

- Operational capacity

- Decision-use

- One Health integration

- Governance and financing improvements

### ii. Course-Correction Design

Identify implementation-sensitive, context-appropriate reforms that can accelerate progress and strengthen national and regional AMR systems.

### iii. Political Commitment Building

Develop realistic, evidence-based, and sustainable political commitments aligned with:

- National priorities

- Fiscal realities

- The Troika process

- Global AMR governance

### iv. Continental Leadership

Position Nigeria—and participating African countries—as thought leaders shaping the next decade of AMR action.

## 4. Expected Outputs

### Technical Outputs

- Seven country stocktake reports

- Investment and financing analysis

- Capacity scorecards

- One Health integration index

- Cross-country synthesis report

- Implementation-sensitive course-correction framework

- Final AMR dashboard

### Political Outputs

- Country-specific commitment packages

- Ministerial briefs

- Donor engagement notes

- Continental AMR position aligned with the Troika process

### Communication Outputs

- 15 website publications

- Conference presentation deck

- Executive summary

- Media-ready messaging

## 5. Expected Outcomes

- Stronger, evidence-based AMR systems across participating countries

- Improved One Health coordination and operational integration

- Clear, realistic, and sustainable political commitments

- Enhanced Africa-wide alignment with global AMR priorities

- Nigeria positioned as a continental leader in AMR governance

## Table 1 — Strategic Objectives Mapped to Outputs

| Objective | How the Plan Delivers It |
| --- | --- |
| Review decade of AMR investments | 7 country stocktakes; investment mapping |
| Assess operational capacity | Surveillance, labs, stewardship, governance reviews |
| Assess decision-use | Policy uptake, regulatory actions, stewardship decisions |
| Strengthen One Health integration | Joint investigations, shared data, governance mapping |
| Identify course-corrections | Implementation-sensitive recommendations |
| Strengthen Nigeria’s global positioning | Troika alignment; continental leadership narrative |
| Inform political commitments | Commitment packages; ministerial briefs |
| Build momentum to conference | 10-day publication cycle |

## 6. Scope and Countries

The stocktake will cover:

- Nigeria (lead country)

- Six additional African countries (add based on readiness and strategic value)

Each country will undergo a structured review across:

- Human health

- Animal health

- Aquaculture

- Environment

- Food safety

- WASH

- Pharmaceutical manufacturing

- Wildlife

- Regulatory systems

- Digital and data system

## 7. Methodology

### Phase 1 — Mobilization & Design (Days 1–20)

- Establish coordination core

- Develop stocktake framework

- Map data sources

- Engage political leadership

### Phase 2 — Data Collection & Country Stocktaking (Days 21–70)

- Investment mapping

- Capacity assessment

- Decision-use analysis

- One Health integration review

### Phase 3 — Analysis & Synthesis (Days 71–105)

- Cross-country comparison

- Gap analysis

- Course-correction design

- Draft political messaging

### Phase 4 — Political Engagement (Days 106–130)

- Ministerial briefings

- Donor engagement

- Commitment package development

### Phase 5 — Finalization & Delivery (Days 131–145)

- Final reports

- Dashboards

- Conference presentation

- Continental messaging

## Table 3 — Summary of Deliverables by Phase

| Phase | Days | Deliverables |
| --- | --- | --- |
| 1 – Mobilization & Design | 1–20 | Stocktake framework; tools; political roadmap |
| 2 – Data Collection | 21–70 | 7 country stocktake reports; investment mapping; capacity scorecards |
| 3 – Analysis & Synthesis | 71–105 | Synthesis report; course-correction framework; dashboards |
| 4 – Political Engagement | 106–130 | Commitment packages; ministerial briefs; donor notes |
| 5 – Finalization & Delivery | 131–145 | Final conference package; presentations; executive summary |

## 8. Communication Strategy: 10-Day Publication Cycle

To maintain visibility and build momentum, a publication will be released on the conference website every 10 days (table 3), including:

- Investment insights

- Surveillance and lab progress

- One Health case studies

- Decision-use examples

- Gap analyses

- Course-corrections

- Political commitment previews

- Final dashboards and scorecards

## Table 3 —15 publications every 10-Days (Quick Reference)

| Publication Day | Title |
| --- | --- |
| Day 10 | Launching Africa’s AMR Decade Review |
| Day 20 | How We Will Measure AMR Progress |
| Day 30 | A Decade of AMR Investments in Africa |
| Day 40 | How AMR Surveillance Has Evolved |
| Day 50 | One Health in Action |
| Day 60 | From Data to Decisions |
| Day 70 | Where Are the Gaps? |
| Day 80 | What the Evidence Tells Us |
| Day 90 | Course-Corrections That Matter |
| Day 100 | Financing the Future |
| Day 105 | Positioning Africa in the Global AMR Agenda |
| Day 115 | Building Political Will |
| Day 125 | Nigeria’s AMR Commitment Package |
| Day 130 | Africa’s Collective AMR Voice |
| Day 140 | The AMR Decade Review |
| Day 145 | Africa’s AMR Future |

This ensures transparency, stakeholder engagement, and sustained political attention.

9. Stakeholders and Partners

- National AMR Coordinating Committees

- Ministries of Health, Agriculture, Environment

- Africa CDC

- Regional economic communities

- Donors and development partners

- Academic and research institutions

- Civil society and professional associations

## 10. Timeline

Total duration: 145 days
Publication frequency: Every 10 days
Conference delivery: Day 145

## Table 4 — Full 145-Day Timeline With 10-Day Website Publications

| Day | Phase | Core Activities | Publication Title | Publication Focus |
| --- | --- | --- | --- | --- |
| 1–10 | 1 | Establish coordination core; define framework; map data sources | #1 Launching Africa’s AMR Decade Review | Why the stocktake matters; countries involved; expectations |
| 11–20 | 1 | Develop tools; political alignment; finalize methodology | #2 Our AMR Progress | Framework, indicators, One Health approach |
| 21–30 | 2 | Begin country deep dives; collect investment data | #3 A Decade of AMR Investments in Africa | Investment trends; Nigeria spotlight |
| 31–40 | 2 | Surveillance, labs, AMU/AMC data collection | #4 Evolution of AMR Surveillance | Surveillance capacity; lab networks |
| 41–50 | 2 | One Health integration assessment | #5 One Health in Action | Joint investigations; shared data |
| 51–60 | 2 | Decision-use assessment; regulatory review | #6 From Data to Decisions | Stewardship; regulatory actions |
| 61–70 | 2 | Identify gaps; bottleneck analysis | #7 Where Are the Gaps? | Workforce, financing, governance, infrastructure |
| 71–80 | 3 | Compare investments vs outcomes; cross-country synthesis | #8 What the Evidence Tells Us | Progress + persistent gaps |
| 81–90 | 3 | Develop course-corrections | #9 Change? Or stay Course? Corrections That Matter | Implementation-sensitive reforms |
| 91–100 | 3 | Financing analysis; sustainability pathways | #10 Financing the Future | Domestic financing; donor alignment |
| 101–105 | 3 | Strategic positioning for global agenda | #11Africa’s Position in the Global AMR Agenda | Troika alignment; global leadership |
| 106–115 | 4 | Ministerial briefings; donor roundtables | #11 Building Political Will | How countries are preparing commitments |
| 116–125 | 4 | Draft commitment packages | #12 Nigeria’s (other countries?) AMR Commitment Package | Evidence-based, realistic commitments |
| 126–130 | 4 | Regional alignment | #13 Africa’s Collective AMR Voice | Unified continental position |
| 131–140 | 5 | Final dashboards; synthesis; country profiles | #14 The AMR Decade Review | Final findings, dashboards, scorecards |
| 141–145 | 5 | Conference delivery | #15 Africa’s AMR Future | Commitments + implementation roadmap |

## 11. Conclusion

This initiative provides a structured, evidence-driven, politically relevant pathway for Nigeria and partner African countries to reflect on a decade of AMR progress, identify practical reforms, and present a unified, compelling narrative at the AMR Conference. It strengthens Africa’s voice in the global AMR arena and ensures that future commitments are grounded in reality, aligned with the Troika process, and capable of delivering measurable impact.