# LAUNCH STRATEGY (MINISTRIES, DONORS, REGIONAL BODIES)

A strategic rollout ensures visibility and adoption.

## Phase 1 — Pre-Launch (4–6 weeks)

- Soft briefings with:

  - Ministries of Health, Agriculture, Environment

  - Africa CDC

  - WHO AFRO

  - FAO & WOAH regional offices

  - Fleming Fund country teams

- Collect endorsements

- Prepare press kit

- Train national focal points on platform use

## Phase 2 — Official Launch

Launch Event (Hybrid Virtual + In-Country)

- Hosted by Ministry of Health + GU-CGHPI

- Keynote from Africa CDC or WHO AFRO

- Demonstration of platform features

- Panel discussion on AMR policy–practice gaps

Communications Push

- Press release

- Social media campaign

- Email blast to regional networks

- Short explainer video

## Phase 3 — Post-Launch Engagement

- Monthly webinars

- Quarterly policy dialogues

- Country-specific onboarding sessions

- Partner spotlight features

- Continuous content updates

## Phase 4 — Institutionalization

- Integrate platform into:

  - National AMR governance structures

  - Africa CDC regional AMR networks

  - Donor coordination mechanisms

- Annual impact report

- Expand to additional countries